## Slide 1
2018/2019
2020
2021
2022 +
Initiation
Strategy
Implementation
Integration
Renewed commitment to Aboriginal outcomes, initiated by Secretary
Establishment of cluster Exec lead for Aboriginal outcomes and new ASO function with Director
Work initiated on development of Aboriginal outcomes strategy and initial Group Plans on a Page
ASO function grows with new permanent and seconded staff, including new managers
OPOC Strategy developed and launched
OPOC MER Framework developed
Further expansion of the ASO function staffing and role
Formal OPOC governance arrangements established
Strategy implementation progressed, including priority workstreams
OPOC MER reporting implemented, including MER Dashboard reports
Integration of OPOC accountability, delivering, monitoring and reporting into cluster Groups
Further development and integration of OPOC MER at cluster level

## Slide 2
Inputs:
MER process guide
MER database of key metrics, data owners and reporting frequencies (Excel)
Previous Dashboard Report
Previous Leadership Team feedback
Activities:
Define the metrics / elements in the Dashboard to be updated
Establish information needs to update the Dashboard
Identify where/who this information needs to come from and how this information is going to be gathered
Plan out the process, activities and timelines required to deliver the updated Dashboard to meet the deadlines required for SteerCo and Leadership Team submission
Identify and allocate resources to carry out the activities
Outputs:
Defined list of key metrics to update for next Dashboard
Delivery plan – with defined process, timelines, resources and responsibilities for delivery
Inputs:
Delivery plan and resources
MER database
OPOC governance (IWG + MERIT)
Previously-identified qualitative ‘stories’ topics and information
Activities:
Send communications to key data owners requesting updated data for key metrics, and any context/commentary
Identify potential 'stories behind the data' based on existing evidence (e.g., IWG presentations, Group POAPs or other initiatives identified through internal engagement or comms)
Contact IWG and MERIT Group members, and any other relevant personnel, to seek further input on relevant initiatives, 'live issues' or 'stories’ for qualitative reporting
Map potential topics for qualitative reporting to the 5 MER headlines
Outputs:
Email communications to key data owners requesting data updates
Initial list/table of identified topics for qualitative reporting, aligning topics to the 5 MER headlines
Inputs:
Delivery plan and resources
MER database
Inputs from data owners (metrics and supporting commentary)
Qualitative information from IWG, MERIT Group and other sources
Activities:
Capture updated metrics and update the OPOC MER database
Review any context/commentary on metrics from data owners and assess how this information might best be captured in the Dashboard
Prioritise and decide on topics for qualitative reporting
Identify any outstanding gaps or issues in quantitative or qualitative data and follow up with relevant contacts
Conduct any data analysis or preparation needed to integrate metrics into the Dashboard (e.g., calculating changes to metrics since last report)
Draft succinct 'stories behind the data' for inclusion into the Dashboard
Outputs:
Updated (and any new) metrics for inclusion in Dashboard
Set of draft new 'stories behind the data’, aligned to the 5 MER headlines
Inputs:
Dashboard template (Powerpoint)
MER database
Updated/new metrics and any context / commentary on data
Draft 'stories behind the data’
MERIT Group
Activities:
Update/add latest metrics (numbers and charts data) in the Dashboard,
Update/add supporting commentary on changes to metrics, emphasising any key changes or trends (re-size and re-position as needed).
Add/update qualitative 'stories' to relevant sections of the Dashboard (re-draft, re-size and re-position as needed, including where necessary moving content to new pages)
Update ‘summary of changes to key metrics’ and 'traffic light' indicators of status/change since the last report
Identify and discuss internally the key messages and discussion points to highlight for Leadership Team
If feasible, engage/share with MERIT Group to seek final input - including around key messages
Outputs:
Draft Dashboard
Further input / feedback from MERIT Group
Inputs:
Draft Dashboard Report
Key messages/discussion points for Leadership Team
Templates for Leadership Team cover presentation (Powerpoint) and cover brief (Word)
Activities:
Finalise framing of key messages and discussion points for the Leadership Team (either related to specific changes in the Dashboard or broader priority issues)
Prepare supporting materials for the SteerCo and Leadership Team, including cover brief and cover presentation with speaking notes
Present Dashboard to OPOC SteerCo and capture any key feedback
Finalise Dashboard, addressing any outstanding information gaps (e.g., late data updates) and any feedback from the SteerCo
Outputs:
Final Dashboard Report
Cover presentation, including summary of changes and framing key messages / discussion points
Cover brief
Planning
Data gathering
Content development
Dashboard integration
Dashboard submission
1
2
3
4
5

## Slide 3
Stage 1a
Stage 1b
Stage 2
Conduct a process evaluation of the Boating Now Program with a focus on Round 3
Satisfy annual ‘health check’ requirements for the Program as part of investment assurance – to enable announcement of Round 4
Highlight any opportunities to improve in Round 4
Finalise a program logic and evaluation framework for the Boating Now Program
Explore opportunities to improve data and indicators for evaluating Boating Now (and other maritime programs)
Finalise Evaluation Plan
Jul – Sep 2021
Sep 2021 – Jan 2022
2022 / 2023
Conduct a process and outcomes evaluation of the Boating Now Program – with a focus on Rounds 3 and 4
Involves delivering the activities set out in the Evaluation Plan
Also expected to include a separate economic evaluation of the Program
1. Context and purpose: Boating Now Program Evaluation

## Slide 4: 4. Our Project Plan
STAGE 1: INCEPTION
Confirm project scope and outcomes, along with individual roles and responsibilities and milestones
Deliverables:
Co-design project planning workshop with Monitoring & Evaluation and Strategy teams
Agreed project plan including key research questions
STAGE 2: DISCOVERY
Comprehensive literature review, including relevant grey literature. The review will identify and triage local and international disaster recovery and resilience programs to be further analysed.
Deliverables:
Draft literature review report
STAGE 3: ANALYSIS
Based on the evidence, create an outcomes, evaluation and implementation framework, documenting key inputs, outputs, and outcomes plus governance suited to NSW.
Deliverables:
Co-design analysis framework workshop
Draft analysis and framework report
STAGE 4: TRANSLATION
Revise draft analysis and framework report. Hold a translation and feedback workshop with Monitoring & Evaluation, and Strategy teams to finalise end product.
Deliverables:
Translation and feedback workshop
Draft report
Final report
Final report
Week 1 (April 11-15)
Week 2-3 (April 18-27)
Week 3-4 (April 28-May 6)
31 May 2022
IPPG will deliver all components of the brief in four structured stages, with the core research activities completed within the required 4-week period, as documented right.
To ensure quality project oversight and risk minimisation, IPPG will schedule weekly Work-in-Progress (WIP) meetings with [client]. We anticipate these will run for 30 minutes and be held via video call.
At IPPG, we are committed to the principle and practices of co-design. As such, we have included two additional workshops beyond the initial consultation with the Monitoring & Evaluation and Strategy teams. This will ensure the project is not only delivering on its objectives, but also gather key stakeholder feedback and insights on the research findings from key parties.